## Progress Report
BART ON-CALL CONSTRUCTION MANAGEMENT SERVICES
Agreement No. 6M8178
PROGRESS REPORT
2026-06-25
Work Plan A.04-02 |  | PO No.: | 71994 |  | Date: |  | 2026-06-25 12:00
Assistant Resident Engineer / Inspector for BART On-Call Construction Management Services |  |  |  | Period: | 2026-06-15 12:00 | to | 2026-06-19 12:00
Describe Work Performed/Accomplished During the Month (List Major Activities)
Summarize Work Completed to Date (Milestones Completed and Dates) by Jordy Peralta
•
Concerns:
N/A
Recommendation of Corrective Action:
N/A
Percent of Work Completed (Physical): |  |  | 0%
Schedule: 24months. Time Passed: 11 months, Remaining 14 months. Comment: No change in schedule | [7 empty] | UPDATE
Cost Forecast at Completion: Current approved budget is |  |  |  | 156185.34 | .
Through this invoice, |  | 0 | 0% | has been billed.
If you have any questions, please contact the undersigned at (510) 282-4932
2026-06-25 12:00
Mahsa Azad, President |  |  |  |  | Date