## Master File (hidden)
| Invoice No. | A.04-02-12
| Invoice Date. | 2026-05-30 12:00
| Period of Service: | from | 2026-04-25 12:00 | to | 2026-05-29 12:00
Prime Cal 1-1
| Amount to data | Previous | hrs | pre hrs
Field | 133815.68 | 122840 | 1619 | 1475
| 147130.0749 | 133895.6
Total | 280945.7549 | 235701.84
SS OT Premium(Jordy) | 1924 | 1924
SS DT Premium(Jordy) | 1776 | 1776
Total | 3700 | 3700
Fixed Fee | 22475.0624 | 20538.25
FCCM Home (0.13% x Direct labor) | 0 | 0
FCCM Field (0.08% x Direct labor) | 0 | 0
Rounding
112776
122925.84
235701.84
1924
1776
3700
18856.1484

## Invoice
Professional Service Agreement Invoice
WSP Invoice No.
Azad Engineering PC
1901 Harrison St. Suite 1100 | [6 empty] | Invoice Date
Oakland, CA 94612 | [6 empty] | 2026-06-15
Mahsa Azad | [6 empty] | Purchase Order No.
(415) 606 -3802 | [6 empty] | 71994
mahsa@azadeng.com | [6 empty] | Sub Invoice Number:
A.04-02-12
WSP Project No.: 30900569.7859
Send To: |  | WSP USA INC
3260 Lone Tree Way, Suite 104
Antioch, CA 94509
Email: candelaria.aldan@wsp.com
Contact Person: |  |  | Candelaria (Cindy) Aldan - Project Financial Analyst
Agreement No: |  |  | 6M8178 |  |  |  | Project No:
Work Plan Title: |  |  | Assistant Resident Engineer / Inspector for Train Control and Communication Projects |  |  |  | 47CJ016, 20LT008
Services for the Period From: | [6 empty] | Terms:
2026-04-25 |  |  |  | to | 2026-05-29 |  | Net 30
Billed Line Items (against Purchase Order Line-Sch, Item/Description
1- 1 | Work Plan A.04-02 | [5 empty] | 26189.7773
|  | TOTAL AMOUNT DUE THIS INVOICE |  |  |  |  | 26189.7773
BILLING SUMMARY:
| Total Work Plan Budget |  |  |  |  | 156185.34
| Total Billed This Period |  |  |  |  | 26189.7773
| Previously Billed Amount |  |  |  |  | 152693.26
| Total Billed to Date Amount |  |  |  |  | 178883.0373
| Amount Remaining |  |  |  |  | -22697.6973
I certify that the direct salaries invoiced herein for this period reflect those amounts actually paid to employees for the time period shown per corporate records.
2026-06-15
Mahsa Azad, |  | ,President | [5 empty] | Date

## Sub Calc _revised
Azad Engineering PC | [6 empty] | Date: | 2026-06-15
INVOICE DETAIL ATTACHMENT | [6 empty] | Invoice No. | A.04-02-12
[7 empty] | Work Plan No. | 0
[5 empty] | Budget | Amount This Period | Previously Billed | Amount To Date | % Expended
Hours to Date
Labor |  | Current | Previous | To Date
Home & Branch (H&B) |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | Budget Increase:
Fringe Benefits on Labor |  |  |  |  | 0 | 0 | 0 | 0 |  | 8 | Target Total | 133202.19
H&B Overhead Pool on Labor |  |  |  |  | 0 | 0 | 0 | 0 |  | 9 | ODC | 4625
|  | 0% |  |  | 0 | 0 | 0 | 0 |  | 10 | Fringe % | 1.09
Field |  | 144 | 1475 | 1619 | 68450 | 10975.68 | 66008 | 76983.68 |  | 11 | Fee % | 0.08
Fringe Benefits |  | 120.6% |  |  | 74610.51 | 13234.4749 | 71948.72 | 85183.1949 |  | 12 | Field | 56963.1357
Field Overhead Pool | [5 empty] | 0 | 0 | 0 |  | 13 | Fringe | 62089.818
|  | 120.6% |  |  | 143060.51 | 24210.1549 | 137956.72 | 162166.8749 |  | 14 | Total Labor | 119052.9537
[10 empty] | 15 | Fee | 9524.2363
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
|  | Total Labor |  |  | 143060.51 | 24210.1549 | 137956.72 | 162166.8749 | 113.4% |  | Grand Total (Check) | 133202.19
Other Direct Costs
[5 empty] | 1680 | 0 | 0 | 0
|  | SS OT Premium(Jordy) | 37/HR | HRS |  |  | 1924 | 1924
|  | SS DT Premium(Jordy) | 74/HR | HRS |  |  | 1776 | 1776
[6 empty] | 0 | 0 | 0
| Car Rental | 0 | Days | 0 | 0 | 0 | 0 | 0
| Lodging | 0 | Nights | 0 | 0 | 0 | 0 | 0
| Meals | 0 | Each | 0 | 0 | 0 | 0 | 0
| Meals First/Last | 0 | Each | 0 | 0 | 0 | 0 | 0
|  | Total Other Direct Cost |  |  | 1680 | 0 | 3700 | 3700 | 0%
Subconsultants:
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
|  | Total Subconsultants |  |  | 0 | 0 | 0 | 0
Project Management:
| PMAC |  | 0% |  | 0 | 0 | 0 | 0
|  | Total PMAC |  |  | 0 | 0 | 0 | 0 | #DIV/0!
Fixed Fee
| Fixed Fee on Labor & Overhead |  | 8% |  | 11444.8408 | 1936.8124 | 11036.54 | 12973.3524
| Fixed Fee for Subconsultants |  | 2% |  | 0 | 0 | 0 | 0
Note: No fixed fee on OH in excess of 150%
|  | Total Fixed Fee |  |  | 11444.8408 | 1936.8124 | 11036.54 | 12973.3524 | 113.4%
| FCCM Home (0.00% x Direct labor) |  | 0.39% |  | 0 | 0 | 0 | 0
| FCCM Field (0.00% x Direct labor) |  | 0.39% |  | 0 | 42.81 | 0 | 42.81
| Rounding |  |  |  |  | 0 | 0 | 0
|  | Total Amount Due |  |  | 156185.3508 | 26189.7773 | 152693.26 | 178883.0373 | 114.5%
|  | Remaining Balance |  |  | -22697.6865
|  |  |  | Original | 156185.3508 |  |  | 12973.3524
|  |  |  | Checked | 0
|  |  |  | Fixed Fee | 0
|  |  |  | Checked | 0
[6 empty] | 26189.7773 | labor
[6 empty] | 0 | expenses

## Progress Report
BART ON-CALL CONSTRUCTION MANAGEMENT SERVICES
Agreement No. 6M8178
PROGRESS REPORT
2026-06-15
Work Plan A.04-02 |  | PO No.: | 71994 |  | Date: |  | 2026-06-15
Assistant Resident Engineer / Inspector for Train Control and Communication Projects |  |  |  | Period: | 2026-04-25 | to | 2026-05-29
Describe Work Performed/Accomplished During the Month (List Major Activities)
Summarize Work Completed to Date (Milestones Completed and Dates) by Jordy Peralta
• | Daily inventory counts of TR4s at LMA.
stored at LMA to ensure installation readiness.
• | Updated Clipper TR4 equipment statuses in BART’s master tracking spreadsheet
“CUBIC-BART_TR4_1599.”
• | Reviewed and audited technical reports submitted by technicians on faregates and
vending machine upgrades.
• | Assisted with packaging and labeling of TR4 equipment returns with Cubic.
•
Concerns:
N/A
Recommendation of Corrective Action:
N/A
Percent of Work Completed (Physical): |  |  | 114.5%
Schedule: 24months. Time Passed: 11 months, Remaining 14 months. Comment: No change in schedule | [7 empty] | UPDATE
Cost Forecast at Completion: Current approved budget is |  |  |  | 156185.34 | .
Through this invoice, |  | 178883.0373 | 114.5% | has been billed.
If you have any questions, please contact the undersigned at (510) 282-4932
2026-06-15
Mahsa Azad, President |  |  |  |  | Date

## Sub Calc (hidden)
Azad Engineering PC | [6 empty] | Date: | 2026-06-15
INVOICE DETAIL ATTACHMENT | [6 empty] | Invoice No. | A.04-02-12
[7 empty] | Work Plan No. | 0 | [8 empty] | REV
[5 empty] | Budget | Amount This Period | Previously Billed | Amount To Date | % Expended |  | Total Billed
Hours to Date
Labor |  | Current | Previous | To Date
Home & Branch (H&B) |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0
Fringe Benefits on Labor |  |  |  |  | 0 | 0 | 0 | 0
H&B Overhead Pool on Labor |  |  |  |  | 0 | 0 | 0 | 0
|  | 0% |  |  | 0 | 0 | 0 | 0
Field |  | 144 | 1475 | 1619 | 68450 | 10975.68 | 122840 | 133815.68
Fringe Benefits |  | 109% |  |  | 74610.5 | 13234.4749 | 133895.6 | 147130.0749
Field Overhead Pool | [5 empty] | 0 | 0 | 0
|  | 109% |  |  | 143060.5 | 24210.1549 | 256735.6 | 280945.7549
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
|  | Total Labor |  |  | 143060.5 | 24210.1549 | 256735.6 | 280945.7549 | 196.4%
Other Direct Costs
[5 empty] | 4625 | 0 | 0 | 0
|  | SS OT Premium(Jordy) | 37/HR | 0/HRS |  | 0 | 1924 | 1924
|  | SS DT Premium(Jordy) | 74/HR | 0/HRS |  |  | 1776 | 1776
[6 empty] | 0 | 0 | 0
| Car Rental | 0 | Days | 0 | 0 | 0 | 0 | 0
| Lodging | 0 | Nights | 0 | 0 | 0 | 0 | 0
| Meals | 0 | Each | 0 | 0 | 0 | 0 | 0
| Meals First/Last | 0 | Each | 0 | 0 | 0 | 0 | 0
|  | Total Other Direct Cost |  |  | 4625 | 0 | 3700 | 3700 | 0%
Subconsultants:
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
|  | Total Subconsultants |  |  | 0 | 0 | 0 | 0
Project Management:
| PMAC |  | 0% |  | 0 | 0 | 0 | 0
|  | Total PMAC |  |  | 0 | 0 | 0 | 0 | #DIV/0!
Fixed Fee
| Fixed Fee on Labor & Overhead |  | 8% |  | 11444.84 | 1936.8124 | 20538.25 | 22475.0624
| Fixed Fee for Subconsultants |  | 2% |  | 0 | 0 | 0 | 0
Note: No fixed fee on OH in excess of 150%
|  | Total Fixed Fee |  |  | 11444.84 | 1936.8124 | 20538.25 | 22475.0624 | 196.4%
| FCCM Home (0.00% x Direct labor) |  | 0% |  | 0 | 0 | 0 | 0
| FCCM Field (0.00% x Direct labor) |  | 0% |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
| Rounding |  |  |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0
|  | Total Amount Due |  |  | 159130.34 | 26146.9673 | 280973.85 | 307120.8173 | 193% |  | 28383.9284 |  | 0 | 28383.9284
|  | Remaining Balance |  |  | -147990.4773 | [5 empty] | 0
[10 empty] | Total s/b zero | 28383.9284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Original | 76844.76 |  |  | 22475.0624
|  |  |  | Checked | -82285.58 |  |  |  |  | Hours s/b zero | 1619
|  |  |  | Fixed Fee | 0
|  |  |  | Checked | 0
[6 empty] | 26146.9673 | labor
[6 empty] | 0 | expenses

## Sub Labor
| Azad Engineering PC |  | Invoice Date: |  | 2026-06-15 |  |  | Max Rate Cap
| LABOR ATTACHMENT |  | Invoice No.: |  | A.04-02-12 |  |  | at $115
|  |  | Work Plan No.: |  | 0 |  |  | Bill Rate Overide
[8 empty] | 2022-01-01 | Total Billed Hours
1 | Classification | Name | Hours | Rate/Hour | Amount | Task No. | Billed $ |  | TOTAL HRS | [8 empty] | 2024-08-01
1 | Home | [5 empty] | 0%
0 |  |  |  |  | 0 |  | 0
0 |  |  |  |  | 0 |  | 0 |  | 0
0 |  |  |  |  | 0 |  | 0 |  | 0
1 | [6 empty] | 0
1 | [6 empty] | 0
1 | [6 empty] | 0
1 | [6 empty] | 0
1 | [6 empty] | 0
1 | [6 empty] | 0
1 | [6 empty] | 0
1 | [6 empty] | 0
0 | SUBTOTAL (HOME) |  | 0 |  | 0 |  | 0
1 | Field | [5 empty] | 120.6%
0 |  |  |  |  | 0 |  | 0 |  | 0
1 | Assistant Resident Engineer-Night-Regular | Jordy Peralta | 144 | 76.22 | 10975.68 |  | 26146.9673 | 13234.4749 | 0
| Assistant Resident Engineer-NIGHT | Jordy Peralta | 0 | 74 | 0
| Assistant Resident Engineer-OT | Jordy Peralta | 0 | 76.22 | 0 |  | 0 | 1936.8124
| Assistant Resident Engineer-DT | Jordy Peralta | 0 | 76.22 | 0 |  | 0
1 |  |  |  |  | 0 |  | 0
1 | SUBTOTAL (FIELD) |  | 144 |  | 10975.68 |  | 26146.9673 | 24210.1549
1
1
1 | TOTAL LABOR |  | 144 |  | 10975.68 |  | 26146.9673 | Labor |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | [6 empty] | 0 | ODC
1 | [6 empty] | 26146.9673 | manual

## Prime ODCs (hidden)
Agreement No. 6M8149 Work Plan No. B.16-01
Table of Other Direct Costs (ODCs)
Month of |  | 0
No. | Invoice Date | Vendor Name | Personnel Name | Invoice Amount | Purpose
0 | 2021-12-08 | WSP | CONSOLACION, Mr. BENJAMIN L |  | ER MILEAGE | IE6881445
0 | 2021-12-08 | WSP | CONSOLACION, Mr. BENJAMIN L |  | ER AUTO - TOLLS/PARKING | IE6881445
0 | 2021-12-08 | WSP | CONSOLACION, Mr. BENJAMIN L |  | ER AUTO - TOLLS/PARKING | IE6881445
0 | 2021-12-08 | WSP | CONSOLACION, Mr. BENJAMIN L |  | ER AUTO - TOLLS/PARKING | IE6881445
0 | 2021-12-08 | WSP | CONSOLACION, Mr. BENJAMIN L |  | ER MILEAGE | IE6881445
0 | 2021-12-16 | WSP | CONSOLACION, Mr. BENJAMIN L |  | ER MILEAGE | IE6881445
0 | 2021-12-16 | WSP | CONSOLACION, Mr. BENJAMIN L |  | ER AUTO - TOLLS/PARKING | IE6881445
0 | 2021-12-16 | WSP | CONSOLACION, Mr. BENJAMIN L |  | ER TICKET FARE | IE6881445
0 | 2021-12-16 | WSP | CONSOLACION, Mr. BENJAMIN L |  | ER MILEAGE | IE6881445
0 | 2021-10-27 | WSP | CONSOLACION, Mr. BENJAMIN L | 0 |  | IE6863524
0 | 2021-10-27 | WSP | CONSOLACION, Mr. BENJAMIN L | 0 | ER MILEAGE | IE6863524
0 | 2021-10-27 | WSP | CONSOLACION, Mr. BENJAMIN L | 0 | ER AUTO - TOLLS/PARKING | IE6863524
0 | 2021-10-27 | WSP | CONSOLACION, Mr. BENJAMIN L | 0 | ER AUTO - TOLLS/PARKING | IE6863524
|  |  | CONSOLACION, Mr. BENJAMIN L SUBTOTAL | 0
Grand Total |  |  |  | 0 |  |  | 0

## ODC (hidden)
Table of Other Direct Costs (ODCs) | [5 empty] | Invoice Date: | 2026-06-15
[6 empty] | Invoice No.: | A.04-02-12
Agreement No. |  | 6M8178 |  |  |  | Work Plan No. | A.04-02
No. | Invoice Date | Vendor Name | Personnel Name | Invoice Amount | Purpose |  |  | Inv #
1 | 2025-06-27 | AZAD | Jordy |  | SS OT Premium (Jordy)
1 |  | AZAD | Jordy |  | SS OT Premium (Jordy)
2 |  | AZAD | Jordy |  | SS DT Premium (Jordy)
Grand Total |  |  |  | 0

## MISC
INVOICE ATTACHMENTS
| • | Signed Progress Report
| • | Receipts for all other direct costs and summary page
|  | • | For travel related costs, please include:
|  | • | Map printout for mileage and purpose of travel
|  | • | GSA per diem page showing destination and rates
|  | • | Detailed hotel receipts (not reservation)
| • | Signed Pre-approvals (travel, overtime etc)
| • | Timesheets (as required by PMs and for Term work plan type)

## JP Week 1 (hidden)
Weekly Timesheet
Azad Engineering PC Timesheet
Employee Name: | Jordy Peralta |  | Week Ending: |  | 2026-05-01
|  |  | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01
Contract / Workplan | Description |  | Sat | Sun | Mon | Tue | Wed | Thur | Fri | TOTAL
6M8178 A.04-01 | Assistant Resident Engineer - Overtime |  | TOTAL: 0
6M8178 A.04-02 | Assistant Resident Engineer - Straight Time-Night |  | Fri: 0; TOTAL: 0
6M8178 A.04-02 | Assistant Resident Engineer - Overtime |  | TOTAL: 0
6M8178 A.04-02 | Assistant Resident Engineer - Doubletime |  | TOTAL: 0
PTO (Sick/Vacation) |  |  | Fri: 8; TOTAL: 8
Holiday |  |  | TOTAL: 0
| TOTAL HOURS |  | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
Submitted by: |  | Approved by:

## JP Week 2
Weekly Timesheet
Azad Engineering PC Timesheet
Employee Name: | Jordy Peralta |  | Week Ending: |  | 2026-05-08
|  |  | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08
Contract / Workplan | Description |  | Sat | Sun | Mon | Tue | Wed | Thur | Fri | TOTAL
6M8178 A.04-02 | Assistant Resident Engineer -Straight Time-Night |  |  |  | 8 | 8 | 8 | 8 | 8 | 40
6M8178 A.04-02 | Assistant Resident Engineer - Overtime |  | TOTAL: 0
6M8178 A.04-02 | Assistant Resident Engineer - Doubletime |  | TOTAL: 0
6M8178 A.04-01 | Assistant Resident Engineer - Doubletime |  | TOTAL: 0
PTO (Sick/Vacation) |  |  | TOTAL: 0
Holiday | ` |  | TOTAL: 0
| TOTAL HOURS |  | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 40
Submitted by: |  | Approved by:

## JP Week 3
Weekly Timesheet
Azad Engineering PC Timesheet
Employee Name: | Jordy Peralta |  | Week Ending: |  | 2026-05-15
|  |  | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15
Contract / Workplan | Description |  | Sat | Sun | Mon | Tue | Wed | Thur | Fri | TOTAL
6M8178 A.04-02 | Assistant Resident Engineer-Straight Time-Night |  |  |  |  | 8 | 8 | 8 | 8 | 32
6M8178 A.04-02 | Assistant Resident Engineer - Overtime |  | TOTAL: 0
6M8178 A.04-02 | Assistant Resident Engineer - Doubletime |  | TOTAL: 0
PTO (Sick/Vacation) |  |  | Mon: 8; TOTAL: 8
Holiday |  |  | TOTAL: 0
| TOTAL HOURS |  | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 40
Submitted by: |  | Approved by:

## JP Week 4
Weekly Timesheet
Azad Engineering PC Timesheet
Employee Name: | Jordy Peralta |  | Week Ending: |  | 2026-05-22
|  |  | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22
Contract / Workplan | Description |  | Sat | Sun | Mon | Tue | Wed | Thur | Fri | TOTAL
6M8178 A.04-02 | Assistant Resident Engineer-Straight Time-Night |  |  |  | 8 | 8 | 8 | 8 | 8 | 40
6M8178 A.04-02 | Assistant Resident Engineer - Overtime |  | TOTAL: 0
6M8178 A.04-02 | Assistant Resident Engineer - Doubletime |  | TOTAL: 0
PTO (Sick/Vacation) |  |  | TOTAL: 0
Holiday |  |  | TOTAL: 0
| TOTAL HOURS |  | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 40
Submitted by: |  | Approved by:

## JP Week6 (hidden)
Weekly Timesheet
Azad Engineering PC Timesheet
Employee Name: | Jordy Peralta |  | Week Ending: |  | 2025-07-04
|  |  | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04
Contract / Workplan | Description |  | Sat | Sun | Mon | Tue | Wed | Thur | Fri | TOTAL
6M8178 A.05-01 | Assistant Resident Engineer-Straight Time |  | TOTAL: 0
6M8178 A.04-01 | Assistant Resident Engineer - Overtime |  | TOTAL: 12
6M8178 A.04-01 | Assistant Resident Engineer - Doubletime |  | TOTAL: 0
PTO (Sick/Vacation) |  |  | TOTAL: 0
Holiday |  |  | Mon: 8; TOTAL: 8
| TOTAL HOURS |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 52
Submitted by: |  | Approved by:

## JP Week 5
Weekly Timesheet
Azad Engineering PC Timesheet
Employee Name: | Jordy Peralta |  | Week Ending: |  | 2026-05-29
|  |  | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29
Contract / Workplan | Description |  | Sat | Sun | Mon | Tue | Wed | Thur | Fri | TOTAL
6M8178 A.04-02 | Assistant Resident Engineer |  |  |  |  | 8 | 8 | 8 | 8 | 32
6M8178 A.04-02 | Assistant Resident Engineer-Night |  | TOTAL: 0
6M8178 A.04-02 | Assistant Resident Engineer - Overtime |  | TOTAL: 0
6M8178 A.04-02 | Assistant Resident Engineer - Doubletime |  | TOTAL: 0
PTO (Sick/Vacation) |  |  | TOTAL: 0
Holiday |  |  | Mon: 8; TOTAL: 8
| TOTAL HOURS |  | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 40
Submitted by: |  | Approved by: