## Overview (hidden)
INVOICE # | B.50-01-30
Agreement No |  | 6M8142
Invoice Date : | 2026-07-08 12:00
Total Hrs
W1 | W2 | W3 | W4 | W5 | Total
144
Period Invoiced: |  | from | 2026-06-01 12:00 | To | 2026-06-30 12:00
6M8142 Architectural and General Engineering Services
Total Contact Amount |  | Amend-1 | Amend-2 | Total | Fully Burdened Billing Rate | 92.5
1381971.85 |  | 0 | 0 | 1381971.85 |  | 92.5
|  | Hrs | Cost
Total Billing to This Period |  | 16 | 31692.4617
Previously Hours and Billed |  | 0 | 1135877.49

## Invoice
Professional Services Agreement Invoice
Azad Engineering PC | [14 empty] | Invoice No.
1901 Harrison St. Suite 1100 | [14 empty] | B.50-01-30
Oakland, CA 94612 | [14 empty] | Invoice Date.
Mahsa Azad | [14 empty] | 2026-07-08 12:00 |  | 159.24
(415) 606-3802 | [14 empty] | Purchase Order No. |  | 159.15
mahsa@azadeng.com | [14 empty] | 1638681 |  | 125.35
[15 empty] | Supplier ID |  | 443.74
Send to: |  |  |  |  | AECOM | [9 empty] | 12345
[5 empty] | 300 Lakeside Drive, Suite 400 | [9 empty] | AECOM Project No.
[5 empty] | Oakland, CA 94612 | [9 empty] | 60723341.03
AECOM Contact Person: |  |  |  |  | Chris Berilla, Program Manager
Agreement No. |  |  | 6M8142 Architectural and General Engineering Services | [8 empty] | BART Project Number(s):
Work Plan Title: |  |  | B.50-03 | [8 empty] | (15CQ002, 15TC002, 45GA000) 15NL004
Period of Service: |  |  | nan | [8 empty] | Terms: |  | Net 30 Days
Billed Line Items (against Purchase Order Line-Sch, Items/Description)
| TOTAL AMOUNT DUE THIS INVOICE: | [7 empty] | 31692.4617 | [8 empty] | =22,702.34 + 436,617.12
| Work Scope No. | PO No. |  | Line # | BART Project No. | PO Amount |  |  | Previous Invoiced |  | Current Invoiced Amount |  | Total Invoiced |  |  | Remaining Balance | 7
| B.50-01 | 1638681 |  | 1 | 15TC002/PJMGT | 179582.83 |  |  | 179582.84 |  | 0
| TOTAL: |  |  |  |  | 1381971.85 |  |  | 1135877.487 |  | 31692.4617 |  | 1167569.949 |  |  | 214401.9083
BILLING SUMMARY
[5 empty] | Total Work Plan Budget |  |  |  |  | 1381971.85
[5 empty] | Previously Billed This Period |  |  |  |  | 1135877.487
[5 empty] | Total Billed This Period |  |  |  |  | 1167569.949
[5 empty] | Amount Remaining |  |  |  |  | 214401.9083
[5 empty] | % of Total Budget Expended |  |  |  |  | 84.49% | [7 empty] | 0
I certify that the direct salaries invoiced herein for this period reflect those amounts actually paid to employees for the time period shown per corporate records and are in conformance with the Advance Agreement.
2026-07-08
|  |  |  | Mahsa Azad, President | [6 empty] | Date
PLEASE REMIT TO :
Check Payment to: | [6 empty] | ACH Payment to:
| Company Name | [6 empty] | Company Name
| Bank Name | [6 empty] | Bank Name
| Address 1 | [6 empty] | Account Number:
| Address 2 | [6 empty] | ABA Number:
Notes: (1) Invoices without a PO number will be rejected by AP. (2) Indicate Remit To address if different from above.

## Sub Calc
z
INVOICE DETAIL ATTACHMENT
Azad Engineering PC | [7 empty] | Date: | 2026-07-08
BART General Engineering Services | [7 empty] | Invoice No. | B.50-01-30
|  |  | Hours to Date |  |  | Budget | Amount This Period | Previously Billed | Amount To Date | % Expended
|  |  | Current | Previous | To Date
Labor |  |  | 144 | 6126 | 6270
Field | [5 empty] | 1381971.85 |  | 0 | 424207.66
Field OH |  | 120.6% |  |  |  | 0 |  | 0 | 456296.72
Field B.50-03 | [5 empty] | 0 | 13281.76 | 1135877.49 | 88073.06
B.50-03_Field OH |  | 120.6% |  |  |  | 0 |  | 0 | 112935.09
[6 empty] | 1279668.81 | 29296.91 | 1052215.62 | 1081512.53
Home
Home Overhead |  | 120.6% |  |  |  | 0 | 0 | 0 | 0
|  | 120.6% |  |  |  | 0 | 0 | 0 | 0
|  |  | Total Labor |  |  | 1279668.81 | 29296.91 | 1052215.62 | 1081512.53 | 84.52%
Overtime (no fee) - Pre-approval is required for all overtime work. | [5 empty] | 0 | 0 | 0 | 0
|  |  | Total Overtime - Premium Cost |  |  | 0 | 0 | 0 | 0
Other Direct Costs
| Misc. - Communications, Reproduction, Printing, Travel |  |  |  |  | 0 | 0 | 0 | 0
|  |  | Total Other Direct Cost |  |  | 0 | 0 | 0 | 0
Subconsultants:
| Subconsultant 1 | [6 empty] | 0 | 0
|  |  | Total Subconsultants |  |  | 0 | 0 | 0 | 0
Fixed Fee
B.50-02 | Fixed Fee on Labor & Overhead |  |  | 8% |  | 0 | 0 | 0 | 69993.44
B.50-02 | Fixed Fee on Labor & Overhead |  |  |  |  | 0 |  | 0 | 0
B.50-03 | Fixed Fee on Labor & Overhead |  |  | 8% |  | 0 | 2343.7528 | 0 | 15716.6328
| Fixed Fee for Subconsultants |  |  | 2% |  | 0 | 0 | 0 | 0
| Note: No fixed fee on OH in excess of 150% | [6 empty] | 0 | 0
|  |  | Total Fixed Fee |  |  | 101605.12 | 2343.7528 | 83366.32 | 85710.0728 | 84.36%
Facilities Capital Cost of Money (FCCM) |  |  | 0.39% |  |  | 0 |  | 0 | 347.3489
|  |  | Total Amount Due |  |  | 1381971.85 | 31692.4617 | 1135877.49 | 1167569.952 | 84.49%
|  |  | Remaining Balance |  |  | 214401.8983
423413.05
423413.05

## Labor Attachment
LABOR ATTACHMENT
Azad Engineering PC
BART General Engineering Services |  |  | Invoice Date: | 2026-07-08
|  |  | Invoice No.: | B.50-01-30
Classification | Category | Hours | Rate/Hour | Amount
Field
Project Manager | Travis Johnson | 0 | 88 | 0 | 0 |  | Total Travis | 0
[9 empty] | Total hours Travis |  | 64 | hours to put
[9 empty] | 15CQ002 | 0.16 | #REF!
| Labor | 0 | 90.11 | 0 |  | 0 | Total Imani |  | 15TC002 | 0.84 | #REF!
Home
B.50-03 - Project (15CQ002, 15TC002, 45GA000) 15NL004
Travis Johnson, Project Manager
| Labor |  | 90.11 | 1441.76 |  | 0
|  | 0 | 92.5 | 11840
| Home | -- | -- | --
B.50-03 - Subtotal |  | 16 |  | 1441.76
Total Labor |  | 144 |  | 13281.76
Overtime - Premium Cost (PRE-APPROVAL REQUIRED)
|  | 0 |  | 0
0
0
0
Total Overtime |  |  |  | 0
Total (Labor+Overtime) |  |  |  | 13281.76
TT
3448.05
45GA000/SUPPT

## Progress Report
Monthly Progress Report
Azad Engineering PC
BART General Engineering Services |  |  |  | Invoice Date: | 2026-07-08
|  |  |  | Invoice No.: | B.50-01-30
Work Plan No: |  | (15CQ002, 15TC002, 45GA000) 15NL004, 15TC002, 15TC012,15CQ002, 15QN004 |  | Agreement: | 6M8142
Work Plan Title: |  | B.50-03 |  | Period: | nan
Work Performed by During this Period:
15CH001 (Millbrae)
• | Performed routine reporting
Percent Work Completed (Physical):
| Item # | Task / Deliverable: |  | % Complete
Cost Forecast at Completion:
| Current approved budget is |  | 1381971.85
| Through this invoice, |  | 1167569.952 | 84.49% has been billed.
Concerns: None at the present.
Recommendation of Corrective Actions: None at the present.
If you have any questions, please contact the undersigned at 415-606-3802 or mahsa@azadeng.com
Submitted by : |  | Travis Johnson, Project Manager
Approaved by : |  | Mahsa Azad, President |  | Date: | 2026-07-08

## Week 1
Azad Engineering PC | [7 empty] | Weekly Timesheet
BART General Engineering Services
Employee Name: | Travis Johnson |  | Week Ending: |  | 2026-06-05
|  |  | 2026-05-30 12:00 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05
Contract / Workplan | Description |  | Sat | Sun | Mon | Tue | Wed | Thur | Fri | TOTAL
6M8142 / B.50-03 | Project Manager |  | Mon: 8; Tue: 8; TOTAL: 16
0
Holiday |  |  | TOTAL: 0
PTO (Sick/Vacation) |  |  | TOTAL: 24
0
0
| TOTAL HOURS |  | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 40
|  | Submitted by: | Wed: Approved by:

## Week 2
Azad Engineering PC | [7 empty] | Weekly Timesheet
BART General Engineering Services
Employee Name: | Travis Johnson |  | Week Ending: |  | 2026-06-12
|  |  | 2026-05-30 12:00 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12
Contract / Workplan | Description |  | Sat | Sun | Mon | Tue | Wed | Thur | Fri | TOTAL
6M8142 / B.50-03 | Project Manager |  |  |  | 8 | 8 | 8 | 8 | 8 | 40
0
Holiday |  |  | TOTAL: 0
PTO (Sick/Vacation) |  |  | TOTAL: 0
0
0
| TOTAL HOURS |  | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 40
|  | Submitted by: | Wed: Approved by:

## Week 3
Azad Engineering PC | [7 empty] | Weekly Timesheet
BART General Engineering Services
Employee Name: | Travis Johnson |  | Week Ending: |  | 2026-06-19
|  |  | 2026-05-30 12:00 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19
Contract / Workplan | Description |  | Sat | Sun | Mon | Tue | Wed | Thur | Fri | TOTAL
6M8142 / B.50-03 | Project Manager |  |  |  | 8 | 8 | 8 | 8 |  | 32
8
Holiday |  |  | TOTAL: 0
PTO (Sick/Vacation) |  |  | TOTAL: 0
0
0
| TOTAL HOURS |  | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 40
|  | Submitted by: | Wed: Approved by:
S

## Week 4
Azad Engineering PC | [7 empty] | Weekly Timesheet
BART General Engineering Services
Employee Name: | Travis Johnson |  | Week Ending: |  | 2026-06-26
|  |  | 2026-05-30 12:00 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26
Contract / Workplan | Description |  | Sat | Sun | Mon | Tue | Wed | Thur | Fri | TOTAL
6M8142 / B.50-03 | Project Manager |  |  |  | 8 | 8 | 8 | 8 | 8 | 40
0
Holiday |  |  | TOTAL: 0
PTO (Sick/Vacation) |  |  | TOTAL: 0
0
0
| TOTAL HOURS |  | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 40
|  | Submitted by: | Wed: Approved by:

## Week 5
Azad Engineering PC | [7 empty] | Weekly Timesheet
BART General Engineering Services
Employee Name: | Travis Johnson |  | Week Ending: |  | 2026-07-03
|  |  | 2026-05-30 12:00 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03
Contract / Workplan | Description |  | Sat | Sun | Mon | Tue | Wed | Thur | Fri | TOTAL
6M8142 / B.50-03 | Project Manager |  | Mon: 8; Tue: 8; TOTAL: 16
0
Holiday |  |  | TOTAL: 0
PTO (Sick/Vacation) |  |  | TOTAL: 0
0
0
| TOTAL HOURS |  | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 16
|  | Submitted by: | Wed: Approved by: